## Slide 1: Sure-Park: Parking lot management system
2016/6/24
5 (Oh!) Team

## Slide 2: Contents
Overview
Project in detail
  Analysis
  Design
  Test
  Management
Lessons learned

## Slide 3: 1. Overview
The project sponsors is Geoff’s Transportation and Parking Services (GPTS LLC).
GPTS LLC own several parking garages and lots, have concerns about inefficiencies in their parking garages and lots.
We have to enable drivers to easily find a parking facility with available parking slots and reserve them.

## Slide 4: 1. Overview
System context diagram
Actors
External System

## Slide 5: 2. Analysis
We analyzed system with
  18 quality attributes
  64 functional requirements
  9 business/technical constraints
We made a baseline with customer (6/14)
Customer said
: “Your requirements seem reasonable to me!”

## Slide 6: 2. Analysis
Significant quality attributes
QA ID | Quality Attributes | Priority | Difficulty
QA-18 | (Usability) User shall be comfortable using parking lot. | H | H
QA-08 | (Extensibility) Owner add a parking lot, maximum 5. | H | M
QA-14 | (Availability) System shall be available for 24 * 7 * 365 without stop. | H | H
QA-17 | (Performance) System shall make a response in 3 seconds. | H | H
QA-15 | (Security) System shall store private data with encryption | M | L
①
②
① what we really focused
② what every team did
③ Relatively easy one
③

## Slide 7: 2. Analysis
Main functional requirements
1. Manage
2. Reserve a slot
3. Park a car

## Slide 8: 3. Design
Early design decisions
ID | Details | Design
CST-13 | The system should use Arduino MEGA 2560 (Wi-Fi enabled). | Independent parking lot
FR-201 | System shall provide at least one method for parking lot reservation. | Independent reservation device
FR-304 | System should be able to receive the confirmation information from driver. | Independent interaction device
Parking lot
Reservation
Device(s)
Interaction
Device(s)
: Identified elements

## Slide 9: 3. Design
Identified roles
Roles | Responsibility | # of reqs. | Assignee
ParkServer | * manage reservation, parking, statistic data * manage authority : owner, driver, attendant | 62 (97%) | Yongchul Park, Jaedo Jin
ParkingLot | * control devices in parking lot by management system's request * monitor sensors in parking lot and send to management system | 16 (25%) | Daedon Jeon
ParkHere | (Owner) * display statistics for parking lot * manage authorities for registered attendants * manage parking lot price, grace period * add/remove parking lots | 17 (27%) | Kimoon Lee
 | (Attendant) * display current status of parking lot * receive notification for emergency | 3 (5%) | 
 | (Driver) * reserve a parking slot with reservation information * display reservation information with confirmation information * can cancel the reservation | 12 (19%) | 
ParkView | * interact with driver at entry gate * display/speak welcome message * receive confirmation information from driver via QR code * display/speak assigned parking slot information | 3 (5%) | Yongchul Park
Notes: # of requirements 는 좋은 기준이 아니다. -> ok, 참고용으로 사용하였다.

## Slide 10: 3. Design
Alternative #1 : client-server #1
Dynamic perspective
Process
Connector (server-client)
Connector (database)

## Slide 11: 3. Design
Alternative #2 : client-server #2 (integrated server)
Dynamic perspective
Process
Connector (server-client)
Connector (database)

## Slide 12: 3. Design
Alternative #3 : shared repository with middleware
Dynamic perspective
Process
Connector
- Asynchronous Bus
- TCP/IP
- No centralized server

## Slide 13: 3. Design
Decision by quality attributes
Dynamic perspective
Alternatives | Promotes | Inhibits | Remarks
Client-Server (#1) | - Extensibility : we can add multiple clients without any modification of program. - Modifiability and reusability : by factoring out common services and having to modify these in a single location, or a small number of locations. | - Availability : Server can be a single point of failure. - Performance : Server can be a performance bottleneck | - We need additional tactics for compensation of availability and performance.
Client-Server (#2) | - Scalability : multiple server can support better performance. - Modifiability and reusability : by factoring out common services and having to modify these in a single location, or a small number of locations. | - Availability : Server can be a single point of failure. | - Server is proved to be a performance bottleneck. Arduino cannot support server role.
Shared repository w/Middleware (#3) | - Modifiability : activities are performed by data, not by services. It removes dependency between services. - Portability and interoperability by defining standard interfaces | - Availability : Repository can be a single point of failure. - Performance : Repository can be a performance bottleneck. This architecture cannot make simultaneous response. | - We need additional tactics for compensation of availability and Performance, especially on response time.

## Slide 14: 3. Design
Early design decision + dynamic perspective
Physical perspective
Physical device
Wireless connection
Arduino
TCP/IP, WiFi
TCP/IP, WiFi
TCP/IP, WiFi
TCP/IP, WiFi
TCP/IP, WiFi
Android
device
Android
device
Laptop
Android
device

## Slide 15: 3. Design
1st Decomposition : functional decomposition
Static perspective
Element
Association

## Slide 16: 3. Design
2nd Decomposition : ParkServer (Layered)
Static perspective
Element
Association

## Slide 17: 3. Design
2nd Decomposition : ParkHere (MVC)
Static perspective
Element
Use
Realization
Generalization

## Slide 18: 3. Design
ParkServer : dynamic perspective
Sub-system design
Process
Connector (post, callback)
Connector (call-return)

## Slide 19: 3. Design
Flexible structure
Database design
Storing statistic data
: occupancy rate
: change history for parking fee, grace period
Storing reservation data
: reservation data created when driver request reservation
: parking data created when parking happened
User data
: user data for actors
: preparation for authority expands
Parking lot data
: data for multiple parking lots
: fee, grace period is stored in here

## Slide 20: 3. Design
Performance
  Manage sampling rate
  Schedule resource
Availability
  Heartbeat
  Timestamp
Security
  Authentication actors
  Encrypt data
Various tactics

## Slide 21: 3. Design
One more thing, usability
  To make our system better, we promote usability
Easy to use, User friendly, Easy to handle…
Various tactics

## Slide 22: 3. Design
Traceability matrix
  We coverer every requirements in design
  We will check the functional coverage by test
Verification

## Slide 23: 4. Test
64 test cases for integration, system level test
  Unit test is done by developer
  Integration test : 26 test cases
  System test : 38 test cases
Test results
Level | # of TC | 6/22 | 6/23 | 6/24
Integration | 26 | 23 | 26 | 26
System | 38 | 14 | 38 | 38
Total | 64 | 37 (58%) | 64 (100%) | 64 (100%)

## Slide 24: 4. Test
Once again, usability
  Reduced time using QR code : 5.3  2.0 seconds
  Customer survey for satisfaction (5 people)
Criteria | 5 Team | Other team
Overall satisfaction | 4.4 | 3
Easy to use | 5 | 3
User friendly | 4 | 3
Easy to handle | 4 | 3
Speed | 5 | 3
Preference | 4 | 3

## Slide 25: 5. Project management
Time log
Chart: Time logs
| 42502 | 42514 | 42521 | 42527 | 42534 | 42541
Planned value | 54 | 124 | 224 | 296 | 388 | 457
Actual cost | 60 | 138 | 252 | 365 | 520 | 765
Earned value | 60 | 122.4 | 207.9 | 281.35 | 358.85 | 456.85
We use pretty much time to complete
272 hour!

## Slide 26: 5. Project management
Variance analysis on schedule and cost
Chart: Variance
| 42502 | 42514 | 42521 | 42527 | 42534 | 42541
sv | 0 | -7.6 | -14.5 | 1.45 | -14.5 | 29
cv | -6 | -15.6 | -28.5 | -39.55 | -77.5 | -147
Typical project style of Korean
Not accurate estimation at planning but no changes on planning
Pouring efforts at the end of project
Finally successful

## Slide 27: 5. Project management
Performance index analysis on schedule and cost
Chart: Performance index
| 42502 | 42514 | 42521 | 42527 | 42534 | 42541
spi | 1.1111 | 0.9871 | 0.92812 | 0.95051 | 0.92487 | 0.99967
cpi | 0.9 | 0.8 | 0.75 | 0.65 | 0.5 | 0.4
Cost-inefficient project

## Slide 28: 5. Project management
Plan was wrong
What we want
What we do

## Slide 29: 5. Project management
Risks are not mitigated, issues are hard to manage
  No experience about Arduino
  No experience about Client-server system
  Not familiar with JSON
  …
Why?
  Learning curve was steeper than we imagined
  Poor estimation made schedule delayed more
  Additional issues came out before we mitigated risks
    e.g. JSON library is not stable…

## Slide 30: 6. Lessons learned
Different people, different experience, and different understanding
Interface, interface, and interface!
Do not believe entirely open source
Used to implement, not used to design
Poor estimation
  project management is hard

## Slide 31: Appendix. Performance tactics
Manage sampling rate : best sampling rate for sensors
  More sampling makes better accuracy
  Less sampling makes better performance
  Best answer is 5 time, between accuracy and performance
Sensor control process : #2
#1
#2
Sometimes sensor goes wrong with consecutive request
We can get stable sensor values

## Slide 32: Appendix. Performance tactics
Schedule resource
  In order to achieve low latency between devices, Arduino controls devices when the messages are arrived, and Arduino also sends the sensor values to server right after it gets.
Network (send/receive)
Control devices
Monitor sensors

## Slide 33: Appendix. Availability
Heartbeat every 5 seconds
  To inform alive, normal, safe and stable
  Server knows device status, and notifies to attendant if failure detected

## Slide 34: Appendix. Availability
Timestamp
  To ensure the message transmission and reception
  Applying between ParkServer and ParkingLot

## Slide 35: Appendix. Security
Authentication actors
  System uses id/password to identify and authenticate actors. When any clients want to connect server, they should send message for authentication.
  The server checks authentication information then grants connection to client. If it fails, server disconnect.

## Slide 36: Appendix. Security
Encrypt data
  Use “XXTEA” encryption algorithm
  Arduino performance issue arise
    It takes more than 5 seconds to encrypt ~200 bytes message.
    Arduino also has a kind of limit to handle long message, experimentally under 200 bytes. But encryption makes message more than 1.5 times to 3 times. We already designed almost 200 bytes sized message, so it is hard to apply encryption thoroughly.
  At this point, we decide to adopt encryption with small values, credit card information and password information.